## CIPReport (3)
Capital Improvement Plan (CIP) Worksheet
Airport Name | San Luis Valley Regional Airport-Bergman Field | [5 empty] | Airport Identifier | ALS
Airport Manager | Will Hickman | [5 empty] | CIP Update | 2018-01-31
Airport Sponsor | Will Hickman | [5 empty] | Engineer/Consultant
Address | PO Box 328, Alamosa, Colorado 81101 USA | [5 empty] | ADO Contact | Ron Niehoff
Phone | (719) 589-4848 | [5 empty] | Fax | (719) 589-1900
Project | FAA Discretionary | FAA State Apportionment | FAA Entitlements | Colorado Discretionary | Local | Passenger Facility Charge | Total Funding | Project Cost Estimate
2019
ILS Maintenance | 0 | 0 | 0 | 0 | 25000 | 0 | 25000 | 25000
Txy A Design |  | 500000 |  | 13157 | 13158 |  | 526315 | 530000
Design in 19 for Const in 21 if Supplemental Discretionary falls through
Master Plan |  |  | 300000 | 7894 | 7895 |  | 315789
Total 2019 | 0 | 500000 | 300000 | 21051 | 46053 | 0 | 867104 | 555000
2020
Fuel Tank Replacement | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000 | 300000
Pulled from 2016
Removed State Funding Due to Funding Shortfall and Federal Match Priority
Airport Parking Lot Phase 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Repay to ??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total 2020 | 0 | 0 | 0 | 150000 | 150000 | 0 | 300000 | 450000
2021
TAXIWAY "A" REHABILITATION | 6000000 | 0 | 150000 | 161842 | 161842 | 0 | 6473684 | 8184000
Needs justification for $6M of DI. Taxiway "A" is exhibiting severe thermal cracking resulting in a maintenance issue and a potential FOD source. This project will rehabilitate/reconstruct the taxiway as required in order to restore the pavement quality. Limited to Tier 1 CDAG funding
Total 2021 | 6000000 | 0 | 150000 | 161842 | 161842 | 0 | 6473684 | 8184000
2022
SRE | 0 | 0 | 150000 | 8333 | 8334 | 0 | 166667 | 0
Total 2022 | 0 | 0 | 150000 | 8333 | 8334 | 0 | 166667 | 0
2023
carryover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024
ARFF Building Expansion |  | 0 | 300000 | 150000 | 150000 | 0 | 600000 | 3000000
Total 2024 |  | 0 | 300000 | 150000 | 150000 | 0 | 600000 | 3000000
2025
No Projects Scheduled
2026
No Projects Scheduled
2027
No Projects Scheduled
2028
No Projects Scheduled
2029
No Projects Scheduled
Long Term
Rehab parking lot |  |  | 0
ILS Equipment Update |  |  | 0 | 225000 | 25000 |  | 250000
Pulled from 2018
Removed State Funding Due to Funding Shortfall and Federal Match Priority
Total Long Term |  |  | 0 | 225000 | 25000 |  | 250000